# The Product Lab Relaunch

## Comprehensive Operations Manual

Teams • Divisions • SOPs • Processes

Document Version: 1.0

Date: March 27, 2026

Status: Active

# Table of Contents

1. Executive Overview

2. Organizational Structure & Divisions

3. The 25 AI Agents: Roles & Responsibilities

4. Standard Operating Procedures (SOPs)

5. Six-Phase Relaunch Execution

6. Requirements Matrix

7. Quality Gates & Approval Criteria

8. Templates & Standards

# 1. Executive Overview

## What This Manual Is

This is the complete operational playbook for The Product Lab D2C relaunch. It documents how a solo founder (Dan) executes a complex brand relaunch using 25 AI agents organized across 9 operational divisions.

This manual is:

Executable—a working guide for daily operations

Transferable—designed so the first hire can understand the system immediately

Locked—no operations change without updating this document

## Company Baseline (As of March 2026)

| Metric | Value |
| --- | --- |
| Annual Revenue | ₹48L (₹4L/month) |
| B2B Share | 80% |
| D2C Target (This Relaunch) | 20% - growth focus |
| Gross Margin | 73% |
| Net Margin | 34% |
| Team Size | Dan (solo) + 25 AI agents |
| Store Location | Cunningham Road, Bangalore |

## Success Criteria for This Relaunch

Launch by Day 60 (May 2026) with 500+ pre-launch subscribers

1.5–2.5% conversion rate on launch traffic

Average Order Value ₹350+

All systems documented and transferable before first hire (Phase 5-6)

Mobile performance: <3s LCP on 4G hard requirement

## How to Use This Manual

For Dan: Reference sections 4–5 (SOPs and Phase execution) weekly.

For the first hire: Read all sections. Section 3 is your role definition.

For AI agents: Read Section 3 (your role) and Section 4 (SOPs that apply to you).

# 2. Organizational Structure & Divisions

The Product Lab operates as 9 operational divisions, each responsible for a functional area of the relaunch. Each division contains 2–4 specialized agents. All agents work in parallel within gates, reporting to Dan (CEO) and Harley (Program Director).

## The 9 Divisions

### Pod A: Command & Accountability

Agents: Claire, Maria

Purpose: Track dependencies, flag blockers, maintain decision log, update program state

### Pod B: Strategy & Insights

Agents: Weiss, Heyward, Jenna

Purpose: Define target customer, brand positioning, product hierarchy

### Pod C: Product & Operations

Agents: Shreyas, Andy

Purpose: Product-market fit validation, catalog structure, physical operations

### Pod D: Creative & Design

Agents: Sean, Joanna, Kurt, Julie

Purpose: Brand identity, UX design, copy, high-fidelity comps

### Pod E: Build & Quality

Agents: Tobi, James

Purpose: Site implementation on Fynd, QA, performance, launch sign-off

### Pod F: Growth & Performance

Agents: Nik, Avinash

Purpose: Launch campaign orchestration, paid/organic channels, optimization

### Pod G: Marketing & Seeding

Agents: Andrew, Chase, Rachel

Purpose: Launch day ops, content scheduling, gift seeding, community

### Pod H: Content Production

Agents: Casey

Purpose: Photography, video, social assets, creative execution

### Pod I: Finance & Ops Infrastructure

Agents: Patrick, Raj, Tony, Lenny

Purpose: Budgets, pricing, fulfillment, shipping, retention

# 3. The 25 AI Agents: Roles & Responsibilities

Each agent has a defined role, phase of responsibility, key outputs, and decision authority. All agents work in parallel within the 6-phase framework. No agent operates without a defined decision right or escalation path.

## Agent Summary Table

| Agent | Pod | Phase | Key Outputs | Authority |
| --- | --- | --- | --- | --- |
| Harley | Pod A | All | Master brief Program timeline | Final artifact approval, Phase gate decisions, esc... |
| Claire | Pod A | 1-6 | Weekly status reports Blocker tracking | Track all work, flag delays >24hrs, manage critica... |
| Maria | Pod A | 1 | Site audit Catalog review | Truth-finding authority on existing operations |
| Weiss | Pod B | 1-2 | Customer insight report Segment analysis | Customer truth; all strategy must ground in resear... |
| Heyward | Pod B | 2 | Brand positioning Message architecture | Approve brand territory and positioning (D-005 loc... |
| Jenna | Pod B | 2 | Product hierarchy Collection structure | Define assortment strategy and catalog hierarchy |
| Shreyas | Pod C | 2-4 | PMF assessment Catalog specs | Validate market fit and product strategy |
| Andy | Pod C | 1-4 | Fulfillment SOP Shipping partner eval | Own operational readiness and supply chain setup |
| Sean | Pod D | 3 | Visual identity Photography brief | Approve all visual direction (D-015 locked) |
| Joanna | Pod D | 3 | Copy system Voice rules | Approve brand voice and all customer-facing langua... |
| Kurt | Pod D | 3 | Sitemap IA document | Own conversion path and information architecture |
| Julie | Pod D | 3 | UI system CSS tokens | Approve all interface design and component specs |
| Tobi | Pod E | 4 | Technical plan Staging site | Own all platform setup, integration, and implement... |
| James | Pod E | 4-5 | QA checklist Test scripts | SOLE authority on launch readiness; no one overrul... |
| Nik | Pod F | 5-6 | Launch narrative Channel plan | Own all growth strategy and launch campaign orches... |
| Avinash | Pod F | 5-6 | Analytics schema Dashboard setup | Own all instrumentation, tracking, and data interp... |
| Andrew | Pod G | 5 | Launch runbook Hour-by-hour ops | Execute launch day operations and real-time respon... |
| Chase | Pod G | 5 | Content calendar Social copy | Own all content strategy and social execution |
| Rachel | Pod G | 5 | Seeding plan Recipient list | Manage gift seeding and early audience cultivation |
| Casey | Pod H | 3-5 | Asset production list Photography brief | Own all creative asset production and coordination |
| Patrick | Pod I | 1-2 | Baseline financials Pricing framework | Approve pricing and financial viability (D-006 loc... |
| Raj | Pod I | 1-4 | Shipping partner eval COD strategy | Own all fulfillment and supply chain operations |
| Tony | Pod I | 5-6 | Launch budget Campaign spend tracking | Manage launch spend and financial tracking |
| Lenny | Pod I | 6 | Retention plan Community strategy | Own post-launch customer retention and LTV optimiz... |

## Detailed Agent Specifications

### Harley — Program Director

Pod: Pod A | Phase: All

Key Outputs:

Master brief

Program timeline

Decision logs

Phase gate approvals

Decision Authority: Final artifact approval, Phase gate decisions, escalation to Dan

### Claire — Operations Lead

Pod: Pod A | Phase: 1-6

Key Outputs:

Weekly status reports

Blocker tracking

Dependency map

Decision Authority: Track all work, flag delays >24hrs, manage critical path

### Maria — Research Librarian

Pod: Pod A | Phase: 1

Key Outputs:

Site audit

Catalog review

Data audit

Decision Authority: Truth-finding authority on existing operations

### Weiss — Customer Insight Lead

Pod: Pod B | Phase: 1-2

Key Outputs:

Customer insight report

Segment analysis

Language patterns

Decision Authority: Customer truth; all strategy must ground in research

### Heyward — Brand Strategist

Pod: Pod B | Phase: 2

Key Outputs:

Brand positioning

Message architecture

Audience definition

Decision Authority: Approve brand territory and positioning (D-005 locked)

### Jenna — Product Lead

Pod: Pod B | Phase: 2

Key Outputs:

Product hierarchy

Collection structure

Hero product list

Decision Authority: Define assortment strategy and catalog hierarchy

### Shreyas — Product Manager

Pod: Pod C | Phase: 2-4

Key Outputs:

PMF assessment

Catalog specs

Product operations

Decision Authority: Validate market fit and product strategy

### Andy — Fulfillment & Packaging Lead

Pod: Pod C | Phase: 1-4

Key Outputs:

Fulfillment SOP

Shipping partner eval

Packaging specs

Decision Authority: Own operational readiness and supply chain setup

# 4. Standard Operating Procedures (SOPs)

These are repeatable workflows that govern how work moves through the organization. Every SOP has an owner, defined steps, approval criteria, and escalation rules.

## SOP 1: Artifact Creation and Review

Owner: Harley (Program Director)

Purpose: Ensure every artifact meets quality standards before use by downstream teams

### Steps:

1. Agent creates artifact in correct phase directory (artifacts/phase-N/) with standard header

2. Agent includes last-updated timestamp, phase, producing agent, status=draft

3. Agent uploads to shared location or workspace folder

4. Harley reviews artifact against quality standards within 24 hours

5. Harley marks status as "review" or requests changes

6. If changes needed: agent revises and repeats step 3-4

7. If approved: Harley marks status as "approved" and date-stamps approval

8. Approved artifact becomes available for downstream teams

Approval Criteria:

Artifact answers one of three questions: What decision does this support? What evidence? What team can act?

All claims have sources (from knowledge base, research, or previous artifacts)

File named per path reference (no custom names)

Standard header present with all fields complete

Status clearly marked (never "approved" until Harley marks it)

## SOP 2: Phase Gate Review

Owner: Harley | Approval Authority: Dan (CEO) + Harley + relevant pod leads

Purpose: Verify a phase is complete before allowing next phase to start

Trigger: All required deliverables for phase marked "approved"

Review Checklist:

All artifacts for the phase exist and are approved

No open blockers >24 hours old unresolved

All decision gates passed (e.g., D-005, D-006, D-015)

Quality assessment: artifact quality meets standard

Downstream readiness: next phase team has what they need

Approval Flow:

Harley writes phase gate review artifact

Harley presents to Dan + relevant pod leads

If GO: Harley marks next phase as ACTIVATED in decision log

If NO-GO: document blockers, reassign owners, retry

## SOP 3: Decision Log Entry

Owner: Claire | Authority: Harley approves, Dan final decision

Purpose: Record all material decisions in append-only log; never modify prior entries

Trigger: A decision affects scope, timeline, budget, strategy, or design

Required Fields for Every Entry:

D-NNN identifier (sequential)

Decision statement (1-2 sentences)

Context (what led to this)

Rationale (why this choice)

Impact (what changes)

Owner (who decided)

Reversibility (can it change?)

Date (YYYY-MM-DD)

Locked Decisions (Cannot Reopen): D-005 through D-017 per CLAUDE.md

## SOP 4: Agent Spawn Protocol

Owner: Harley | Execution: Harley spawns agents as sub-agents

Purpose: Activate an agent with full context so they can work independently

Pre-Spawn (Same Session):

Read agent persona from knowledge/02-AGENT-PERSONAS.md

Read agent system prompt from knowledge/09-AI-AGENT-PROMPTS.md

Read relevant upstream artifacts (phase prior)

Identify primary deliverable for this phase

Read applicable handoff document

Spawn Context (Provided to Agent):

Agent persona and working style

Locked brand decisions (D-005, D-006, D-007, D-011, D-015)

Company facts (knowledge/16-COMPANY-FACTS.md)

Upstream artifacts (prior phase outputs)

Handoff brief with explicit instructions

Current program state (knowledge/26-CURRENT-STATE.md)

## SOP 5: Handoff Protocol

Owner: Completing agent | Receiver: Next phase or next agent

Required Handoff File Contents:

from: and to: agent names

Artifact(s) being delivered (full paths)

Quality assessment (what is complete, what is draft)

Explicit instructions for receiver (what to do next)

Known blockers or dependencies

Date and approval status

File naming: phase-N-to-M-handoff.md or YYYY-MM-DD-[from]-to-[to].md

# 5. Six-Phase Relaunch Execution

Timeline: Day 0 (March 15) through Day 60 (May 26, 2026)

## Phase 1: Audit & Truth-Finding

Duration: Days 0-10 (Mar 15-25)

Pod Leads: Maria, Weiss, Patrick, Raj

Outputs: Site audit, customer insights, competitor research, baseline financials, problem statement

Phase Gate: Top 5 problems defined; hero categories hypothesized

## Phase 2: Brand Strategy

Duration: Days 10-20 (Mar 25 - Apr 5)

Pod Leads: Heyward, Jenna, Shreyas, Patrick

Outputs: Positioning, message architecture, product hierarchy, pricing framework

Phase Gate: Brand territory locked (D-005, D-006 approved)

## Phase 3: Creative & Design

Duration: Days 20-35 (Apr 5-20)

Pod Leads: Sean, Joanna, Kurt, Julie, Casey

Outputs: Visual identity, copy system, UX/IA, UI components, hi-fi designs, asset list

Phase Gate: All creative approved (D-015, D-016); Dan receives photography brief

## Phase 4: Build & Merchandising

Duration: Days 35-50 (Apr 20 - May 5)

Pod Leads: Tobi, James, Andy, Dan

Outputs: Staging site live, products uploaded with photos/copy, QA checklist complete

Phase Gate: James signs off: all P0/P1 issues resolved; site ready for Phase 5

## Phase 5: Launch Campaign

Duration: Days 50-60 (May 5-15)

Pod Leads: Nik, Andrew, Chase, Rachel, Casey, Eli

Outputs: Content live, seeding shipped, email/SMS flows active, launch day executed

Phase Gate: GO/NO-GO decision; site live to traffic

## Phase 6: Optimize & Learn

Duration: Days 60-90 (May 15 onward)

Pod Leads: Eli, Nik, Lenny, Avinash

Outputs: 30-day performance review, A/B test roadmap, retention plan, Drop 2 strategy

Phase Gate: Data-driven optimization in motion

## Parallel Workstreams Within Phases

Multiple pods work simultaneously within each phase, coordinated by Claire and Harley:

Phase 1: Maria (audit) || Weiss (insights) || Patrick (financials) || Raj (logistics)

Phase 2: Heyward (positioning) || Jenna (products) || Shreyas (PMF) || Patrick (pricing)

Phase 3: Sean (visual) || Joanna (copy) || Kurt (UX) || Julie (UI) || Casey (assets)

Phase 4: Tobi (build) || James (QA) || Andy (ops) || Dan (photography + copy)

Phase 5: Nik (growth) || Andrew (launch ops) || Chase (content) || Rachel (seeding) || Eli (flows)

Phase 6: Eli (retention) || Nik (optimization) || Avinash (analytics) || Lenny (community)

# 6. Requirements Matrix

Every division has specific tool, data, integration, and team requirements to succeed.

## Technical & Platform Requirements

| Division | Primary Tool / Platform | Critical Integrations |
| --- | --- | --- |
| Pod E (Build) | Fynd / Commerce.com | Razorpay, Shiprocket, GA4, Clarity |
| Pod F (Growth) | Nik needs Instagram/YouTube access | Klaviyo/Mailchimp, MSG91/Gupshup (WhatsApp) |
| Pod G (Marketing) | Figma, Canva | Instagram, Facebook, Pinterest APIs |
| Pod H (Content) | Adobe Suite or Figma | Photo storage, Canva for social |
| Pod I (Ops) | Razorpay dashboard, Shiprocket portal | GST compliance, COD settlement |
| All Pods | Shared artifact storage | Decision log, status tracking, artifact versioning |

## Data & Content Requirements

| Owner | What Needed | By When |
| --- | --- | --- |
| Dan (CEO) | Hero product photography (dark bg, phone camera, 15+ SKUs) | Day 35 (Phase 4 start) |
| Dan (CEO) | Product copy for hero SKUs using voice rules | Day 35 (Phase 4 start) |
| Casey + Dan | 10 pre-launch Reel/content pieces | Day 45 (Phase 5 start) |
| Rachel | Design Yatra contact list + 20+ identified gift recipients | Day 45 |
| Raj | Live Shiprocket account + test COD transactions | Day 30 |
| Tobi | Fynd store credentials and GST setup | Day 26 (Phase 4 day 1) |

## Budget & Cost Constraints

Bootstrap model: No tool cost >₹5,000/month unless revenue-generating

Escalation: Any budget decision >₹5K/month goes to Dan

| Service | Model | Est. Monthly Cost |
| --- | --- | --- |
| Platform (Fynd/Commerce.com) | Included with Razorpay setup | ₹0-500/month |
| Payments (Razorpay) | Transaction % + settlement fees | ~₹3K-5K/month at launch |
| Shipping (Shiprocket) | Per-shipment + COD fees | ~₹1K-3K/month estimated |
| Email/SMS (Klaviyo or Mailchimp) | Usage-based | ₹0-2K/month at launch |
| Analytics (GA4 + Clarity) | Free tier | ₹0 |
| Figma (existing) | Team license | ₹1,500/month (shared) |

# 7. Quality Gates & Approval Criteria

## Universal Artifact Quality Standard

Every deliverable artifact must answer these 3 questions before approval:

What decision does this artifact support?

What evidence or reasoning does it rely on?

What downstream team can act on it immediately?

## Phase Gate Checklist

### Phase 1→2

Top 5 commercial/UX problems identified & sources cited

Hero category hypotheses defined (card stickers, attitudes, pins)

Customer language patterns captured (voice baseline)

Baseline revenue, margin, cost structure documented

No open blockers

### Phase 2→3

Primary customer clearly defined (persona)

Brand territory differentiated vs. competitors

Pricing approved by Dan (D-006)

Product hierarchy and hero collections selected

No strategic ambiguity for design team

### Phase 3→4

Visual direction approved by Dan (D-015)

Voice rules locked; all copy contexts written

UX/IA complete with wireframes & user journey

UI component system specced for build

Hi-fi page designs approved for 8 pages

Asset production list provided to Dan

All creative artifacts marked "approved"

### Phase 4→5

Staging site live on Fynd with correct theme/colors

Hero products uploaded with real photos & copy (15+)

Razorpay processing tested (at least 3 real test orders)

Shiprocket AWBs generating (COD end-to-end tested)

GA4 event tracking validated for 5+ key events

Mobile <3s LCP on 4G confirmed

James QA sign-off: no P0 or open P1 issues

3+ collections live with correct products

### Phase 5→6

Site live to paid & organic traffic

Email/SMS flows deployed (welcome, cart abandonment, post-purchase)

10 pre-launch content posts published (Instagram/YouTube)

20+ gift recipients identified and seeded

500+ email subscribers captured

Launch day runbook executed without critical incidents

Monitoring dashboards live

### Phase 6 (30-day review)

Conversion rate, AOV, repeat rate measured

Top 10 optimizations identified from data

3+ A/B tests in flight

Drop 2 strategy defined

Retention cohorts tracking

Decision on hiring made based on scale

# 8. Templates & Standards

## Artifact Header Standard

Every artifact must start with:

<!-- last-updated: YYYY-MM-DD -->

# [Title]

**Phase:** [1-6]

**Producing Agent:** [Name]

**Date:** YYYY-MM-DD

**Status:** draft | review | approved

**Reviewer:** [Name]

## File Naming Conventions

Artifacts: artifacts/phase-{N}/{descriptive-name}.md

Handoffs: phase-{N}-to-{M}-handoff.md or YYYY-MM-DD-[from]-to-[to].md

Decisions: decision-log.md (append-only, D-NNN format)

Status: status/weekly-status.md (timestamped sections)

## Decision Log Entry Format

| ID | Decision | Date | Owner | Status |

| D-NNN | [1-2 sentence decision statement] | YYYY-MM-DD | [Owner] | Active/Resolved |

# Appendix: Key Numbers All Agents Must Know

| Metric | Value |
| --- | --- |
| Target Conversion Rate | 1.5-2.5% |
| Target AOV | ₹350+ |
| Target Launch Subscribers | 500+ |
| Pre-launch Gift Target | 20+ products |
| Free Shipping Threshold | ₹499 |
| COD Minimum | ₹299 |
| Prepaid Discount | ₹30 |
| Annual Revenue (Current) | ₹48L (₹4L/month) |
| B2B Mix (Current) | 80% |
| D2C Target (This Relaunch) | 20% |
| Gross Margin | 73% |
| Net Margin | 34% |
| Store Rent | ₹1L/month |
| Mobile LCP Hard Limit | <3s on 4G |
| Launch Target | May 26, 2026 (Day 60) |

# Document Governance

Prepared by: Harley (Program Director)

Approved by: Dan (Founder/CEO)

Date: March 27, 2026

This manual is locked. Changes require written amendment signed by Dan. Every session update must reflect in an updated version date.